## Detail
BOND 2003 FFE
For the Month Ended February 28, 2006
Bond 2003 Series I Projects | Budget | Actual/ Adjusted Amount | Paid to Date | Balance to Complete | Variance | Committed | Remaining
Elementary Special Ed
Grounds Equipment | 1500 | 0 | 0 | 0 | 1500 | 0 | 0
Custodial Equipment | 5000 | 4200 | 4131 | 69 | 800 | 4131 | 69
Maintenance Equipment | 11000 | 0 | 0 | 0 | 11000 | 0 | 0
General Furniture | 85000 | 55000 | 54188 | 812 | 30000 | 54188 | 812
Special Ed Loose Equipment | 40000 | 39000 | 38999 | 1 | 1000 | 38999 | 1
Lounge/Clinic (Fridge, etc) | 6000 | 5300 | 5288 | 12 | 700 | 5288 | 12
Other | 2500 | 0 | 0 | 0 | 2500 | 0 | 0
TOTAL | 151000 | 103500 | 102606 | 894 | 47500 | 102606 | 894
Existing High School
Office Area | 40000 | 10905 | 10905 | 0 | 29095 | 10905 | 0
Special Ed | 5000 | 40000 | 0 | 40000 | -35000 | 0 | 40000
Eng/Mfr Addition | 30000 | 106000 | 99651 | 6349 | -76000 | 99651 | 6349
Fitness Area | 45000 | 46500 | 46532 | -32 | -1500 | 46453 | 47
P.E. Office | 3000 | 9500 | 9531 | -31 | -6500 | 3019 | 6481
Seating | 0 | 15960 | 15960 | 0 | -15960 | 0 | 15960
Other Projects | 10000 | 12000 | 11920 | 80 | -2000 | 11920 | 80
TOTAL | 133000 | 240865 | 194499 | 46366 | -107865 | 171948 | 68917
Millennium Tech Wing
Loose FFE | 85000 | 72500 | 72440 | 60 | 12500 | 72440 | 60
Technology Furniture | 65000 | 63200 | 63159 | 41 | 1800 | 63159 | 41
Custodial Equipment | 5500 | 4100 | 4050 | 50 | 1400 | 4050 | 50
Alarms/etc. | 15000 | 10800 | 10795 | 5 | 4200 | 10795 | 5
Shop Equipment | 10000 | 9600 | 9571 | 29 | 400 | 9571 | 29
Other | 0 | 4300 | 4281 | 19 | -4300 | 4281 | 19
TOTAL | 180500 | 164500 | 164296 | 204 | 16000 | 164296 | 204
Bartlett
Clocks/Other | 2500 | 3250 | 3264 | -14 | -750 | 3264 | -14
Salem
General Furniture | 33650 | 31600 | 31677 | -77 | 2050 | 31677 | -77
Other | 1350 | 0 | 0 | 0 | 1350 | 0 | 0
TOTAL | 35000 | 31600 | 31677 | -77 | 3400 | 30468 | -77
Maintenance/Transportation Bldg
Custodial Equipment | 1000 | 1000 | 0 | 1000 | 0 | 0 | 1000
Maintenance Equipment | 3000 | 3000 | 0 | 3000 | 0 | 0 | 3000
General Furniture/Shelving | 75000 | 75000 | 0 | 75000 | 0 | 0 | 75000
Signage/Alarms/etc. | 6000 | 6000 | 0 | 6000 | 0 | 0 | 6000
Lounge (Fridge, etc) | 2500 | 2500 | 0 | 2500 | 0 | 0 | 2500
Equipment/Tools | 29523 | 30000 | 0 | 30000 | -477 | 0 | 30000
TOTAL | 117023 | 117500 | 0 | 117500 | -477 | 0 | 117500
Other
Design Fees (Not to Exceed) | 278005 | 278005 | 222587 | 55418 | 0 | 278005 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 278005 | 278005 | 222587 | 55418 | 0 | 278005 | 0
New High School
Lump Sum Budget-Unallocated | 3642500 | 3642500 | 3245871 | 396629 | 0 | 3245871 | 396629
TOTAL | 3642500 | 3642500 | 3245871 | 396629 | 0 | 3245871 | 396629
TOTALS | 4539528 | 4581720 | 3964800 | 616920 | -42192 | 3996458 | 584053
Note on C11: SLCS: IDS award of $75,551 remainder for adds
Note on C28: SLCS: $75842 award plus adds
Note on C29: SLCS: award of $63,159, balance for adds
Note on C21: SLCS: 40k for weights (Larry), 2.5k misc, 2.5k teacher station(Chuck) ADDED MAT FOR 8120
Note on C20: SLCS: estimate from Chuck
Note on C18: SLCS: Larry's office is about 15K, need to confirm outer area cost.
Note on C19: SLCS: nothing known at this time
Note on C42: SLCS: Per Estimate from Ann
Note on C32: SLCS: someone needs to order
Note on C10: SLCS: List from Charlie, plus $2,150 for extra, 75% 2000, 25% 2003
Note on C9: SLCS: Tri-County bid of $18,073, 3/4 bond 2000, 1/4 bond 2003
Note on C8: SLCS: Waiting for confirmation from Chris
Note on C47: SLCS: Per Ann Green estimate
Note on C31: SLCS: update to entire building system
Note on E42: SLCS: Per Estimate from Ann
Note on G42: SLCS: Per Estimate from Ann
Note on E20: SLCS: some budgeted in Tech, $26K est. for Phase 3