## A
Capital Site Improvement Projects
Status Report as of May 31, 2005
|  | Project |  |  |  | Estimated |  | Adjusted | Amount |  |  |  | Code
|  | Code |  | Responsible |  | Completion | Budget | Project | Paid To | Balance To | Budget |  | D=done
Location |  | Number |  | Party | Task Description | Date | Amount | Amount | Date | Complete | Variance | Comments | I=incomplete
District Wide | 0 | - | 1 | Contractor | Playground Site Upgrades |  | 10000 | 17500 | 17462 | 38 | -7500 | In Durant Project | I
| 0 | - | 2 | Contractor | Signage | Completed | 2000 | 2000 | 3275 | -1275 | 0 |  | I
| 0 | - | 3 | Contractor | Landscape construction or Renovation | Completed | 6000 | 3250 | 5180 | -1930 | 2750 |  | I
| 0 | - | 4 |  | Contingency funds for general site improvements |  | 10000 | 6000 | 17725 | -11725 | 4000
[5 empty] | DISTRICT WIDE TOTAL |  | 28000 | 28750 | 43642 | -14892 | -750
High School | 1 | - | 1 | Contractor | Add irrigation - Baseball JV | Completed | 7000 | 7000 | 0 | 7000 | 0 |  | C
| 1 | - | 2 |  | Add irrigation - Softball Freshman & JV |  | 7000 | 7000 | 0 | 7000 | 0
| 1 | - | 3 | Both |  | 4/1/98 | 0 | 0 | 0 | 0 | 0 | Waiting on paint order | I
| 1 | - | 4 |  |  |  | 0 | 0 | 0
[5 empty] | HIGH SCHOOL TOTAL |  | 14000 | 14000 | 0 | 14000 | 0
Middle School Campus | 3 | - | 1 |  |  |  | 0 | 0 | 0 | 0 | 0
[5 empty] | MIDDLE SCHOOL TOTAL |  | 0 | 0 | 0 | 0 | 0
Bartlett Elem. | 6 | - | 1 | Contractor | Add irrigation - main entrance | Completed | 6000 | 5500 | 5500 | 0 | 500 |  | I
| 6 | - | 2 |  | Install/remove structures |  | 4500 | 3700 | 3683 | 17 | 800
| 6 | - | 3 |  | Playground equipment match |  | 2500 | 2500 | 4012 | -1512 | 0
| 6 | - | 4 |  |  |  | 0 | 0 | 0 | 0 | 0
| 6 | - | 5 |  |  |  | 0 | 0 | 0 | 0 | 0
[5 empty] | BARTLETT ELEMENTARY TOTAL |  | 13000 | 11700 | 13195 | -1495 | 1300
Brummer Elem. | 7 | - | 1 | Contractor | Playground equipment match |  | 2500 | 2500 | 0 | 2500 | 0 |  | I
| 7 | - | 2 |  |  |  | 0 | 0 | 0 | 0 | 0
[5 empty] | BARTLETT ELEMENTARY TOTAL |  | 2500 | 2500 | 0 | 2500 | 0
Dolsen Elem. | 8 | - | 1 | Contractor | Remove old backstop and structure |  | 3000 | 4250 | 4250 | 0 | -1250 |  | C
| 8 | - | 2 |  | Playground equipment match |  | 2500 | 2250 | 1991 | 259 | 250
| 8 | - | 3 |  |  |  | 0 | 0 | 0 | 0 | 0
| 8 | - | 4 | Contractor |  | TBD | 0 | 0 | 0 | 0 | 0
[5 empty] | DOLSEN ELEMENTARY TOTAL |  | 5500 | 6500 | 6241 | 259 | -1000 | 0 | 0
Kent Lake Elem. | 9 | - | 1 | Contractor | Playground equipment match |  | 2500 | 4750 | 5763 | -1013 | -2250 |  | C
| 9 | - | 2 | Contractor |  | TBD | 0 | 0 | 0 | 0 | 0
[5 empty] | KENT LAKE ELEMENTARY TOTAL |  | 2500 | 4750 | 5763 | -1013 | -2250 | 0 | 0
Salem Elem. | 10 | - | 1 | Staff | Playground equipment match | Ongoing | 2500 | 2500 | 0 | 2500 | 0 | On hold due to bond work | C
| 10 | - | 2 |  |  |  | 0 | 0 | 0 | 0 | 0
| 10 | - | 3 |  |  |  | 0 | 0 | 0 | 0 | 0
[5 empty] | SALEM ELEMENTARY TOTAL |  | 2500 | 2500 | 0 | 2500 | 0
Sayre Elem. | 11 | - | 1 | Contractor | Playground Equipment Match |  | 2500 | 2500 | 0 | 2500 | 0 | On hold due to bond work | I
| 11 | - | 2 |  | Add irrigation - bus loop |  | 5000 | 5000 | 0 | 5000 | 0
| 11 | - | 3 |  |  |  | 0 | 0 | 0 | 0 | 0
[5 empty] | SAYRE ELEMENTARY TOTAL |  | 7500 | 7500 | 0 | 7500 | 0
Admin Building | 20 | - | 1 | Contractor |  |  | 0 | 0 | 0 | 0 | 0 |  | C
| 20 | - | 2 |  |  |  | 0 | 0 | 0 | 0 | 0
[5 empty] | ADMINISTRATION BUILDING TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Maint/Trans | 8 | - | 1 | Contractor | Parking | Completed | 7500 | 7500 | 0 | 7500 | 0 | Could not Finance | I
[5 empty] | TRANSPORTATION BUILDING |  | 7500 | 7500 | 0 | 7500 | 0
[5 empty] | TOTALS |  | 83000 | 85700 | 68841 | 16859 | -2700 | 0 | 0
Note on J13: Jim Graham: less 8300 plus 2413, 3990, and 2993.

## Sheet1
T/A Balance | 68841
Report Balance | 68841
0

## Playground Match
Playground Equipment Match
B A L A N C E A V A I L A B L E
| 1996-97 | 1997-98 | 1998-99 | 1999-00 | 2000-01 | 2001-02 | 2002-03 | 2003-04 | 2004-05
Bartlett | 2500 | 2150 | 4650 | 6600 | 9100 | 11600 | 14100 | 16600 | 15088
Brummer | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 5000 | 7500
Dolsen | 2500 | 2500 | 385 | 385 | 9235 | 14235 | 16735 | 19235 | 21735 | -1991
Kent Lake | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 5000 | 1737
Salem | 2500 | 2500 | 2730 | 2730 | 5230 | 7730 | 10230 | 12730 | 15230 | 17730
Sayre | 2500 | 2500 | 155 | 155 | 2655 | -1753 | 747 | 3247 | 5747
Dolsen-District Match |  |  |  | 385 | 2135 | 4635 | 7135 | 9635 | 12135
Dolsen-PTO contribution |  |  |  | 0 | 7100 | 9600 | 9600 | 9600 | 9600 | 0
[8 empty] | 19235 | 21735
Note on J5: SLCS: should be getting invoice for $8k, pay half.
Note on F7: SLCS: 7100 contributed by PTO
Note on G7: SLCS: $2,500 contributed by PTO
Note on K7: SLCS: $3,982 bill, borrowed $1991 from matching dollars
Note on J8: SLCS: payment made 9/2004
Note on J15: SLCS: actual equipment cost $26,368 so PTO paid an additional $4,633